## Grant chart Template
Q-3: Your company is launching their support login website which goes live in 3 months. Come up with a schedule for your testing phase. Plot your schedule using the attached Grant chart template.
Task Name | Start date | End date | Duration (days) | Days remaining | Percent compleate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Test Plan Creation | 2023-04-10 | 2023-04-17 | 7 | 0 | 80% | bar: Week 1
Review and Approval of Test Plan | 2023-04-17 | 2023-04-24 | 7 | 0 | 90% | bar: Week 2
Test Case Development | 2023-04-25 | 2023-05-09 | 21 | 0 | 90% | bar: Week 2 to Week 4
Test Environment Setup | 2023-05-02 | 2023-05-09 | 7 | 0 | 100% | bar: Week 3
Test Data Preparation | 2023-05-02 | 2023-05-18 | 14 | 0 | 100% | bar: Week 3 to Week 4
Test Execution Phase 1 | 2023-05-18 | 2023-06-08 | 21 | 0 | 50% | bar: Week 4 to Week 6
Bug Reporting | 2023-05-18 | 2023-06-08 | 21 | 0 | 90% | bar: Week 4 to Week 6
Bug Fixing | 2023-06-09 | 2023-06-30 | 21 | 0 | 100% | bar: Week 7 to Week 9
Test Execution Phase 2 | 2023-06-09 | 2023-06-30 | 21 | 0 | 50% | bar: Week 7 to Week 9
Regression Testing | 2023-06-10 | 2023-07-01 | 21 | 0 | 90% | bar: Week 10 to Week 12
Test Results Analysis | 2023-06-10 | 2023-07-01 | 21 | 0 | 70% | bar: Week 1 to Week 11

## Login page Test
Q-2:Your development team plans to launch a support website where customers can log in with a username and password and see the status of the order they placed.
Write 10 test cases to ensure that the website is working properly, identify the type of test case you have written( black box, white box, regression, performance, integration)
Test Case Description: | Website is working properly and user able to access or login his account | The website is functioning correctly, and unauthorized users are unable to register or log in | Authorized user is able to log in successfully | Unauthorized users should receive an appropriate error message. | User is able to view current status of the order | Unauthorize user cnn't view the status of someone else's order | How to behave the system when a large number of user enter at a time | The website is functioning correctly, allowing users to perform their desired actions, and resulting in their satisfaction. | How well does the system perform when integrating with another system? | Check the stability and functionality of all existing features.
Test Case ID: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Testcase Name: | User Registration Validation | User Registration fail | User Login | User Login Validation | View Order Status | Order Status Security | Concurrent Users | Website Responsiveness | Database Integration | Regression Testing
Tester's Name | Hasina A. Twhida | Hasina A. Twhida | Hasina A. Twhida | Hasina A. Twhida | Hasina A. Twhida | Hasina A. Twhida | Hasina A. Twhida | Hasina A. Twhida | Hasina A. Twhida | Hasina A. Twhida
Priority : | High | High | High | High | High | High | Medium | High | High | High
Date Tasted | 2023-04-09 | 2023-04-09 | 2023-04-09 | 2023-04-09 | 2023-04-09 | 2023-04-09 | 2023-04-09 | 2023-04-09 | 2023-04-09 | 2023-04-09
Type of Test Case | Black box | Black box | Black box | Black box | Black box | Black box | Performance | Performance | Integration | Regression
Name of feature/module : | Login screen | Login screen | Login screen | Login screen | Current status of the order | Current status of the order | How first website or screen open or landing on the login page | Functionality of the website | Shopping cart functionality | User interface
Summary of test One line of the purpose of the test | Ensure that the user is registered. | Ensure that unauthorized users cannot log in or are restricted from accessing the login page. | Make sure that user is log in | Make sure that unauthorize user can not login or restricted for login page | Make sure that user can view their order status | Make sure that unauthorize user can't view the order status page and secure customer privacy | Make sure that user can able to do some thing | Make sure that user can able to do some thing | Make sure that sytem does what ever he has to do . | Existing all of features.
Pre-condition(s) : | How to reach the login page | How to reach the login page | How can you access login website on your device | How to reach the login website on your device | How to reach the order status page | How to reach the order status page | How to reach the website on your device | How to reach the website on your device | How to reach the website on your device | How to reach the website on your device
Dependencies: | Ensure that your internet connection is working. | Ensure that your internet connection is working. | Ensure that your internet connection is working. | Ensure that your internet connection is working. | Ensure that your internet connection is working. | Ensure that your internet connection is working. | Make sure that your internet connection is workinng . | Ensure that your internet connection is working.. | Make sure that your internet connection is workinng . | Ensure that your internet connection is working.
Step Details: | Input a valid username and password | Input an invalid username and password | Input valid username and password | Input invalid username and password | Log in with valid username and password | Log in with valid username and password | Simulate a large number of concurrent user | Perform user actions such as clicking links, filling out forms, and loading pages | Log in with valid username and password | After a software update, perform the above test cases again
Expected Result : | Verify that the user account is created successfully | Verify that the user account creation fails with appropriate error message | Verify that user is able to log in successfully | Verify that the user is unable to log in with an appropriate error message when incorrect login credentials are entered. | Verify that user is able to view the status of their order(s) | Verify that user is unable to view the status of someone else's order | Verify that the website can handle the traffic without crashing or slowing down | Verify that the website responds quickly to user actions and page loads | Verify that the website is able to retrieve and display the correct order status from the back-end database | Verify that previously working features continue to work correctly
Status Pass: | Pass | Fail | Pass | Fail | Pass | Fail | Pass | Pass | Pass | Pass
Comments: | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A